## Slide 1: ClassMic C1 project charter
Draft authorization
Test student phones as instructor-controlled microphones to improve classroom audibility and participation. Proposed pilot: 14 weeks, three classrooms, six weeks live and an AED 60,000 ceiling.
Success measure | Proposed target | Evidence
Session setup | At least 90% within 2 minutes | Timed session records
Speaking access | At least 90% audible within 3 seconds of approval | Request and audio timing
Audio delay | Median of 700 ms or less | Latency tests
Audibility | At least 75% positive feedback | Student and instructor survey
Privacy and security | Zero critical incidents | Incident and control records
Draft targets and limits require confirmation against the approved ClassMic A2 and B2 outputs.
Notes: C1 draft charter. Sources: ClassMic_Phase_C_Project_Charter.docx, sections 1 to 4 and 10. All values are carried forward from that existing draft. Approved ClassMic A2/B2 outputs and sponsor approval were not supplied. CampusCrew_Phase_B_Business_Case.docx concerns a different project. Success targets require confirmation of definitions, measurement window, sample sufficiency and acceptance owner.

## Slide 2: Scope and delivery
Included scope
Browser and QR join, temporary sessions, speaking queue, instructor controls, one active phone microphone, room speaker output, user guidance and pilot evaluation.
Exclusions
Recording, stored audio or transcripts, voice identification, speech-based attendance or grading, simultaneous microphones, permanent profiles, remote learning and campus-wide rollout.
High level requirements
Explicit microphone permission, instructor approval, push to talk and mute/end controls. Preserve privacy and accessible participation, with a physical microphone or instructor-repeat fallback.
Deliverables and milestones
W1 charter and kickoff. W2–3 requirements. W4–6 prototype. W7–8 testing and user acceptance. W9–14 six-week pilot, evaluation and sponsor decision.
Schedule and resource commitments remain subject to confirmation.
Notes: Sources: ClassMic_Phase_C_Project_Charter.docx, sections 3, 4 and 10. The relative milestones are proposed and have no confirmed calendar dates. The final pilot includes the six weeks from Week 9 through Week 14. Recording and persistent audio or transcript storage remain excluded.

## Slide 3: Authority and confirmation
Teaching and Learning, instructors, students, IT/AV, privacy and security, accessibility, Finance and Procurement.
Stakeholders
Feedback, delay, incompatible devices, privacy misuse and low adoption. Test rooms, train users and retain a fallback.
Initial risks
Stable Wi-Fi, speakers, compatible phones and available reviewers. Proposed limits: 14 weeks, three rooms, AED 60,000.
Assumptions
Approved ClassMic A2/B2, role appointments, dates, rooms and evaluation method. Student input and genuine brainstorming photos are pending.
To confirm
Proposed leadership
Sponsor: Dean of Academic Affairs. Project manager: Nurtore Arynuruly. Technical lead: Temiko Machavariani.
On approval, the PM manages daily work within agreed limits. The sponsor approves material changes. Control owners approve readiness.
The available CampusCrew business case is for a different project. ClassMic approval is unverified.
Notes: Sources: ClassMic_Phase_C_Project_Charter.docx, stakeholder register, governance, constraints and authorization sections. Role appointments and approval signatures have not been verified. Actual individual input from Temiko Machavariani and Nurtore Arynuruly and real photos of charter brainstorming were not supplied. The package contains labeled forms for the team to complete.