## Slide 1: ClassMic project charter
C1 Draft course authorization
Test student phones as instructor-controlled microphones. Revised A2 and B2 support a limited prototype, controlled evaluation and a later pilot decision.
Objective | Proposed target | Evidence
O1 Complete scope | Five stories and all Must checks | Acceptance record
O2 Practical workflow | 9/10 setups within 2 min 27/30 speaking trials within 3 sec | Scripted timed trials
O3 Audibility | At least 75% positive feedback At least 5 volunteer reviewers | Counts and sample limits
O4 Control and privacy | No unauthorized transmission No saved audio or transcripts | Misuse and storage checks
One-way audio delay target: 95th percentile at most 150 ms.
Notes: Sources: ClassMic aspiration, business case and charter. The targets cover scope completion, usable setup and speaking, perceived audibility, and instructor control. Ready-speaker trials measure time from instructor approval to audible speech. Audio transport delay is measured separately, with median and 95th percentile reported and a proposed 95th percentile target of 150 milliseconds.

## Slide 2: Scope and delivery
Included scope
Temporary browser sessions, QR or code join, speaking queue, one approved phone microphone, speaker output, recovery and evaluation.
Exclusions
Live teaching deployment, recording, transcripts, persistent profiles, grading, attendance, simultaneous microphones and paid production infrastructure.
Requirements
Explicit microphone permission, instructor approval and push to talk. Mute, disconnect and end must stop audio. Preserve an alternative speaking route.
Milestones
Plan review by 19 September. Sprint 1 on 20–26 September. Sprint 2 on 27 September–3 October. Closeout and final presentation on 4–9 October.
Two weekly construction sprints, after the planned review on 19 September.
Notes: Source: revised C1 charter. The course scope contains five priority stories and two one-week sprints. The earlier 14-week classroom pilot is outside the current course authorization. The proposed schedule places planning review by 19 September, followed by the two build sprints and a closeout review by 9 October.

## Slide 3: Authority and open decisions
Student speakers and listeners, instructors and the project team. Technical and accessibility reviewers participate if available.
Stakeholders
Feedback, delay, incompatible devices, unwanted transmission and limited time. Test early and retain a fallback.
Initial risks
100 student hours: Temiko 54 and Nurtore 46. AED 0 incremental cash through reuse of existing equipment.
Resources
Course sponsor and authorization, equipment access, volunteer availability and the proposed 100-hour team capacity.
To confirm
Planning responsibilities
Course instructor: acceptance authority. Nurtore Arynuruly: project manager. Temiko Machavariani: technical lead.
The PM coordinates daily work. The instructor reviews material scope and schedule changes. No university spending authority is implied.
No live deployment or paid commitment is authorized by this draft.
Notes: Sources: ClassMic charter and business case. Nurtore coordinates the project and Temiko leads technical development. Proposed effort is 54 hours for Temiko and 46 for Nurtore. Course authorization, the named sponsor and access to equipment and reviewers remain open. The instructor reviews material scope or schedule changes.