## Slide 1: ClassMic project charter
C1 Draft course authorization
Test student phones as instructor-controlled microphones. Revised A2 and B2 support a limited prototype, controlled evaluation and a later pilot decision.
Objective | Proposed target | Evidence
O1 Complete scope | Five stories and all Must checks | Acceptance record
O2 Practical workflow | 9/10 setups within 2 min 27/30 speaking trials within 3 sec | Scripted timed trials
O3 Audibility | At least 75% positive feedback At least 5 volunteer reviewers | Counts and sample limits
O4 Control and privacy | No unauthorized transmission No saved audio or transcripts | Misuse and storage checks
Selected one-way delay target: 95th percentile at most 150 ms. Formal course acceptance remains open.
Notes: Sources: revised ClassMic A2, B2 and C1. The C1 LMS brief https://lms.mbzuai.ac.ae/mod/assign/view.php?id=38960 requests a draft with explicit confirmations, at most two pages and three slides. All measures are proposed. Ready-speaker trials measure time from instructor approval to audible speech. Transport delay is separate, with median and 95th percentile reported and a selected 95th percentile target of 150 milliseconds.

## Slide 2: Scope and delivery
Included scope
Temporary browser sessions, QR or code join, speaking queue, one approved phone microphone, speaker output, recovery and evaluation.
Exclusions
Live teaching deployment, recording, transcripts, persistent profiles, grading, attendance, simultaneous microphones and paid production infrastructure.
Requirements
Explicit microphone permission, instructor approval and push to talk. Mute, disconnect and end must stop audio. Preserve an alternative speaking route.
Milestones
Plan review by 19 September. Sprint 1 on 20–26 September. Sprint 2 on 27 September–3 October. Closeout and final presentation on 4–9 October.
Two weekly construction sprints, after the planned review on 19 September.
Notes: Source: revised C1 charter. The course scope contains five priority stories and two one-week sprints. The earlier 14-week classroom pilot is outside the current course authorization. The proposed schedule places planning review by 19 September, followed by the two build sprints and a closeout review by 9 October.

## Slide 3: Authority and open decisions
Student speakers and listeners, instructors and the project team. Technical and accessibility reviewers participate if available.
Stakeholders
Feedback, delay, incompatible devices, unwanted transmission and limited time. Test early and retain a fallback.
Initial risks
Proposed 100 student hours and AED 0 new cash spending through reuse. Confirm equipment, volunteers and capacity.
Resources
Formal course approval, resource access and genuine team evidence. Original individual input and the brainstorming proposal are included.
To confirm
Planning responsibilities
Course instructor: acceptance authority. Nurtore Arynuruly: project manager. Temiko Machavariani: technical lead.
The PM coordinates daily work. The instructor reviews material scope and schedule changes. No university spending authority is implied.
No live deployment or paid commitment is authorized by this draft.
Notes: Source: revised C1 charter. Formal course acceptance, the named sponsor and resource access require confirmation. The package includes Temiko’s original SMART note and a charter planning worksheet. An original image of the team discussing the charter remains to be supplied.