# ClassMic Charter Planning

Options and proposed decisions

Temiko Machavariani and Nurtore Arynuruly   |   BUS 2010   |   10 September 2026

ClassMic will test whether instructor-controlled phone microphones improve the audibility of student contributions. The planning options focus on a small prototype that fits the course schedule.

# Starting concept

Temiko’s in-class SMART note proposes one active phone microphone, instructor control and reuse of existing equipment. Its goals include low delay and at least 75% positive feedback. The charter retains these aims and narrows the course project to controlled prototype evaluation.

# Planning options

| Planning choice | Alternatives | Proposed direction and reason |
| --- | --- | --- |
| What problem is worth testing? | A quiet question, a listener at the back, or time spent passing a microphone. | Test the hypothesis that phone microphones improve audibility when a student’s unaided voice is difficult to hear. |
| What could solve it? | Instructor repetition, an existing physical mic, a commercial phone-mic system, or a small browser prototype. | A small browser prototype allows direct comparison with the current speaking process. A commercial system remains an option for a future institutional pilot. |
| Who controls the microphone? | Open microphones or an instructor-approved queue. | One approved push-to-talk speaker, with mute, removal and end controls. This reduces interruption and makes control testable. |
| How much can the course deliver? | A live campus pilot or a controlled two-sprint build. | Five priority stories in two weekly sprints. Live deployment and a six-week classroom pilot remain outside the course project. |
| What will count as success? | A polished demo alone or measured acceptance evidence. | Acceptance checks, setup and activation timings, a 150 ms one-way delay target, volunteer feedback and zero critical control defects. |

# Proposed charter decisions

The proposed scope covers five priority user stories across two weekly sprints, with 100 student hours and AED 0 incremental cash assuming existing resources are available. Nurtore coordinates the project and Temiko leads technical work. Course approval and resource availability remain open project decisions.