## Slide 1: ClassMic aspiration
Quiet questions may need repeating or a microphone. We have not yet measured how often this happens in our classes.
Problem
Students request a turn from their phones. An approved speaker uses the room speaker without passing a microphone.
Proposed value
Test whether students can use phone microphones easily and whether the room can hear them clearly.
Concept
Two weekly build sprints and controlled evaluation. A live classroom pilot needs a later decision.
Boundary
A2 Classroom participation
Make student questions easier for the whole room to hear while the instructor controls speaking turns.
The course project will test a small browser prototype using existing equipment.
Temiko Machavariani and Nurtore Arynuruly BUS 2010
Notes: The prototype will test audibility and ease of use in a controlled setting. Local user feedback is needed before a classroom pilot.

## Slide 2: Stakeholders
Students
Students need an easy way to request a turn and hear one another. A physical microphone or instructor repetition remains available.
Instructors
Instructors need to approve a speaker, mute the microphone and end a session without disrupting discussion.
Project team
Proposed roles: Temiko leads development and testing. Nurtore coordinates requirements, delivery and evaluation.
Review and support
The course instructor reviews deliverables. Technical and accessibility advisers may help if a room test can be arranged.
Team capacity and reviewer availability remain planning assumptions.
Notes: The proposed role split puts development and testing with Temiko Machavariani and requirements and delivery coordination with Nurtore Arynuruly. The schedule assumes both have enough time for their assigned work.

## Slide 3: Proposed success measures
Prototype evaluation
Build five priority user stories in two weekly sprints. Evaluate the prototype against these targets.
Measure | Target | Evidence
Prototype scope | Five stories and all required checks | Acceptance record
Setup and speaking | 9/10 setups within 2 min 27/30 speaking trials within 3 sec | Scripted timed trials
Audibility | At least 75% positive feedback At least 5 volunteer reviewers | Feedback counts
Control and privacy | No unauthorized transmission No saved audio or transcripts | Misuse and storage checks
One-way audio delay target: 95th percentile at most 150 ms.
Notes: Record positive and total feedback counts. Measure one-way audio delay separately from the time between instructor approval and audible speech. The delay target is a 95th percentile of 150 ms or less.