## Slide 1: ClassMic project charter
C1 Draft course authorization
Test student phones as instructor-controlled microphones. Revised A2 and B2 support a limited prototype, controlled evaluation and a later pilot decision.
Objective | Proposed target | Evidence
O1 Complete scope | Five stories and all Must checks | Acceptance record
O2 Practical workflow | 9/10 setups within 2 min 27/30 speaking trials within 3 sec | Scripted timed trials
O3 Audibility | At least 75% positive feedback At least 5 volunteer reviewers | Counts and sample limits
O4 Control and privacy | No unauthorized transmission No saved audio or transcripts | Misuse and storage checks
Targets and approvals require confirmation. Report transport delay separately from speaking activation.
Notes: Sources: revised ClassMic A2, B2 and C1. The C1 LMS brief https://lms.mbzuai.ac.ae/mod/assign/view.php?id=38960 requests a draft with explicit confirmations, at most two pages and three slides. All measures are proposed. Ready-speaker trials measure time from instructor approval to audible speech. Transport delay is separate, with median and 95th percentile reported and a threshold awaiting confirmation.

## Slide 2: Scope and delivery
Included scope
Temporary browser sessions, QR or code join, speaking queue, one approved phone microphone, speaker output, recovery and evaluation.
Exclusions
Live teaching deployment, recording, transcripts, persistent profiles, grading, attendance, simultaneous microphones and paid production infrastructure.
Requirements
Explicit microphone permission, instructor approval and push to talk. Mute, disconnect and end must stop audio. Preserve an alternative speaking route.
Milestones
D review by 19 September. Sprint 1 on 20–26 September. Sprint 2 on 27 September–3 October. Closeout and final presentation on 4–9 October.
Two weekly construction sprints. The proposed early start needs instructor confirmation.
Notes: Sources: revised C1 charter and D1-D3 plan. The course scope contains five priority stories and two one-week sprints. The earlier 14-week funded classroom pilot is outside the current course authorization. The proposed schedule requires D review by 19 September and instructor permission to start E construction before the upload area opens on 26 September.

## Slide 3: Authority and open decisions
Student speakers and listeners, instructors and the project team. Technical and accessibility reviewers participate if available.
Stakeholders
Feedback, delay, incompatible devices, unwanted transmission and limited time. Test early and retain a fallback.
Initial risks
Proposed 100 student hours and AED 0 new cash spending through reuse. Confirm equipment, volunteers and capacity.
Resources
A2/B2/C1 approval, roles, dates, audio threshold and genuine brainstorming evidence. Individual inputs are handled separately.
To confirm
Proposed responsibilities
Course instructor: acceptance authority. Nurtore Arynuruly: project manager. Temiko Machavariani: technical lead.
The PM coordinates daily work. The instructor reviews material scope and schedule changes. No university spending authority is implied.
No live deployment or paid commitment is authorized by this draft.
Notes: Sources: revised C1 charter and evidence record. The course instructor is a proposed acceptance authority whose name and agreement remain unconfirmed. The team has not supplied original charter brainstorming images. Individual input is handled separately at the user request. No approval, funding, live deployment or completed testing is implied.