CONNECT THEME

CampusCrew

Phase B — Business Case: Should We Invest?

TEAM MEMBERS  •  Temiko Machavariani  •  Nurtore Arynuruly

| DECISION REQUESTED Authorize a controlled MVP pilot | PLANNING DATE 4 September 2026 |
| --- | --- |
| PILOT SCOPE One campus • 500 invited students | TIME / FUNDING 12 weeks • AED 92,000 cap |

RECOMMENDATION: GO — PILOT ONLY Approve a 12-week custom MVP pilot capped at AED 92,000. Do not approve campus-wide production until local demand, safe adoption, and operating effort are measured against the decision gates on the final page.

# 1. Opportunity and proposed solution

The decision problem. Students can often see clubs and events, yet still struggle to turn interest into a first, low-pressure in-person interaction—especially when they are new, commute, have limited time, or do not already know an organizer. Existing channels advertise broadly; they do not reliably form a small group around a shared goal, time, and place.

CampusCrew. A verified, mobile-first campus service that creates temporary ‘crews’ of 3–6 students for a specific real-world activity: a study sprint, portfolio build, coding practice, sport, language exchange, or campus event. A 60-second intent card captures goal, availability, preferred language, and accessibility needs; the service proposes a suitable crew and public on-campus meetup. It has no infinite feed, follower counts, or public popularity metrics.

# 2. Why the case merits a pilot

- Strategic alignment — strengthens belonging, peer learning, student experience, and cross-discipline collaboration while producing measurable participation data.

- External need signal — WHO’s 2025 commission reported that roughly 17–21% of people aged 13–29 experience loneliness, and emphasized practical, scalable social-connection interventions [1].

- Intervention logic — the U.S. Surgeon General recommends peer-led programs, supportive environments, and regular opportunities for connection in education settings [2]. CampusCrew operationalizes those principles around real activities.

- Evidence caution — the U.S. Department of Education found mixed overall effects for college social-belonging interventions, although one commuter-heavy randomized study showed promising retention evidence [3]. This uncertainty supports a measured pilot, not a full rollout.

# 3. Expected value

| Student value | Institution value | Learning value |
| --- | --- | --- |
| Faster path from interest to a useful, face-to-face connection; lower friction for new and commuting students. | A focused engagement channel with attendance and satisfaction evidence—not just clicks or impressions. | A low-cost test of demand, safety, matching rules, and support load before any larger investment. |

# 4. Alternatives appraisal

Scoring scale: 1 = weak, 5 = strong. Weights total 100%. Scores are decision-team judgments based on the stated pilot assumptions; they are not vendor quotations or measured outcomes.

| Criterion | Weight | 1 Improve current | 2 Buy commercial | 3 Custom MVP |
| --- | --- | --- | --- | --- |
| Strategic alignment | 15% | 3 | 4 | 5 |
| Expected benefits | 20% | 2 | 4 | 5 |
| Cost / value | 15% | 4 | 2 | 3 |
| Feasibility | 10% | 5 | 4 | 3 |
| Schedule | 10% | 5 | 3 | 3 |
| Security, privacy & risk | 10% | 4 | 3 | 4 |
| Operational support | 10% | 3 | 3 | 4 |
| Stakeholder adoption | 10% | 2 | 3 | 4 |
| Weighted total | 100% | 67 / 100 | 66 / 100 | 80 / 100 |

## Option findings

1 — Improve current process (AED 28k–45k/year). Use existing email, forms, calendars, clubs, and messaging groups with a part-time coordinator. Fast and low-risk, but fragmented, manual, difficult to scale, and unlikely to solve the ‘first small group’ problem. Suitable only as a short baseline/control.

2 — Buy a commercial platform (AED 160k–300k Year 1 allowance). A product such as CampusGroups already offers groups, events, registration, attendance, analytics, mobile access, and integrations [4]. It is broad and mature, but public pricing is not provided; procurement, configuration, vendor dependency, and paying for unused modules reduce fit for a narrowly defined pilot. A supplier quote and privacy review would be mandatory.

3 — Build a focused custom MVP (AED 92k cap). Best fit to the differentiated workflow and smallest viable data footprint. It takes more design and technical ownership, but can reuse university identity, email/calendar, and analytics services. A rules-based matcher should be used first; optional AI may summarize free-text interests into tags, but must not make safety, disciplinary, or academic decisions.

# 5. Pilot economics and schedule

| Cost element | AED | Basis |
| --- | --- | --- |
| Discovery, service design & usability | 12,000 | Interviews, workflow, prototype tests |
| MVP engineering & integration | 46,000 | Responsive web app, SSO, calendar/email |
| Security, privacy & QA | 12,000 | Threat review, testing, consent and logs |
| Pilot operations & student ambassadors | 10,000 | Recruitment, moderation, support |
| Hosting, monitoring & tools | 6,000 | 12-week pilot allowance |
| Contingency | 6,000 | Approx. 7% of base cost |
| Total authorization cap | 92,000 | Stop-spend limit; change control required |

Budget note: planning allowances are exclusive of VAT and assume existing campus SSO, email/calendar, meeting spaces, and one internal product owner. Ongoing production cost is not authorized. Retention ROI remains a hypothesis; the break-even formula is AED 92,000 ÷ average net contribution per retained student.

| Wk 1–2 | Wk 3–6 | Wk 7–8 | Wk 9–11 | Wk 12 |
| --- | --- | --- | --- | --- |
| Validate need + privacy | Build + integrate | Test + recruit | Live pilot | Evaluate + decide |

# 6. Recommended pilot design

| MVP must include | Explicitly out of scope |
| --- | --- |
| Verified SSO; optional intent card; transparent crew suggestions; organizer-confirmed public campus meetups; reminders; QR attendance; three-question pulse survey; reporting, moderation and incident workflow. | Public social feed; follower counts; open direct messages; external users; precise GPS tracking; health or academic-record data; paid events; autonomous AI decisions; ranking students by popularity or ‘fit’. |

# 7. Principal risks and controls

| Risk | Preventive / response control | Owner | Trigger |
| --- | --- | --- | --- |
| Low student adoption | Co-design with target users; ambassadors; seed useful crews; test onboarding weekly. | Product owner | <25% activation by day 14 |
| Safety or misconduct | Verified accounts; public venues; code of conduct; report/block; escalation pathway. | Student Affairs | Any high-severity report |
| Privacy or breach | Consent, minimization, encryption, role access, logs, 90-day post-evaluation deletion. | Privacy / IT | Unauthorized access or loss |
| Biased or exclusionary matching | Rules first; explain matches; opt-out/edit preferences; accessibility and language testing. | Product owner | >15-point outcome gap |
| Support load exceeds value | Self-service help; triage queue; weekly defect review; cap cohorts. | Service owner | >0.25 FTE for 2 weeks |

Privacy requirement. UAE Federal Decree-Law No. 45 of 2021 provides a framework for personal-data governance and generally prohibits processing without consent except in specified cases [5]. The pilot must document purpose, lawful basis, consent, access rights, security controls, retention, deletion, and any processor arrangements before recruitment.

# 8. Success measures and decision gates

| Measure | Pilot threshold | Evidence |
| --- | --- | --- |
| Activation | ≥35% of 500 invitees | Verified onboarding log |
| Match acceptance | ≥50% of proposed crews | Accepted / proposed |
| Real-world participation | ≥75 unique attendees | QR check-in + audit sample |
| Connection outcome | ≥60% report one useful new connection | Anonymous post-meetup pulse |
| Speed | Median ≤7 days to accepted crew | Event timestamps |
| Safety / operations | 0 unresolved critical incidents; ≤0.25 FTE | Incident + support logs |

GO to production discovery: zero unresolved critical incidents, the safety/operations gate is met, and at least four of the five engagement/outcome thresholds are achieved. REVISE: no critical incident, but only two or three thresholds are met; run one corrected cohort within the existing cap. NO-GO: fewer than two thresholds are met, support is disproportionate, or a severe control failure cannot be acceptably remediated.

DECISION GO with Option 3: a tightly scoped custom MVP pilot. Preserve Option 1 as the comparison baseline; request a commercial quote only if the pilot proves demand for broader club, event, and engagement-management capabilities.

## Sources

[1] World Health Organization, Commission on Social Connection report and 2025 release. Open source

[2] U.S. Surgeon General, Our Epidemic of Loneliness and Isolation (education recommendations, 2023). Open source

[3] U.S. Department of Education, What Works Clearinghouse: Social Belonging (2022). Open source

[4] Ready Education, CampusGroups product capabilities (accessed 4 Sep 2026). Open source

[5] UAE Government, Data protection laws: Federal Decree-Law No. 45 of 2021 (accessed 4 Sep 2026). Open source