## Slide 1: ClassMic project charter
C1 Draft course authorization
Test student phones as instructor-controlled microphones through a limited prototype and controlled evaluation. Use the findings to assess a future pilot.
Objective | Proposed target | Evidence
O1 Complete scope | Five stories and all Must checks | Acceptance record
O2 Practical workflow | 9/10 setups within 2 min 27/30 speaking trials within 3 sec | Scripted timed trials
O3 Audibility | At least 75% positive feedback At least 5 volunteer reviewers | Counts and sample limits
O4 Control and privacy | No unauthorized transmission No saved audio or transcripts | Misuse and storage checks
Temiko Machavariani and Nurtore Arynuruly BUS 2010
Notes: The scope and performance figures are proposed acceptance targets. No test outcomes are asserted. Speaking activation includes the time from instructor approval until a ready speaker is audible.

## Slide 2: Scope and delivery
Included scope
Temporary browser sessions, QR or code join, speaking queue, one approved phone microphone, speaker output, recovery and evaluation.
Exclusions
Live teaching deployment, recording, transcripts, persistent profiles, grading, attendance, simultaneous microphones and paid production infrastructure.
Requirements
Explicit microphone permission, instructor approval and push to talk. Mute, disconnect and end must stop audio. Preserve an alternative speaking route.
Milestones
Plan review by 18 September. Sprint 1 on 19–25 September. Sprint 2 on 26 September–2 October. Closeout and final presentation on 3–9 October.
Two weekly construction sprints, after the planned review on 18 September.
Notes: Two weekly sprints end on 2 October to leave the product report ready before 3 October at 00:00. Live classroom deployment requires separate authorization.

## Slide 3: Governance and resources
Student speakers and listeners, instructors and the project team. Technical and accessibility reviewers participate if available.
Stakeholders
Feedback, delay, incompatible devices, unwanted transmission and limited time. Test early and retain a fallback.
Initial risks
100 student hours: Temiko 54 and Nurtore 46. AED 0 incremental cash through reuse of existing equipment.
Resources
Delivery assumes course acceptance, available equipment, volunteer reviewers and 100 hours of team capacity.
Assumptions
Planning responsibilities
Course instructor: acceptance authority. Nurtore Arynuruly: project manager. Temiko Machavariani: technical lead.
The PM coordinates daily work. The instructor reviews material scope and schedule changes. No university spending authority is implied.
No live deployment or paid commitment is authorized by this draft.
Notes: The proposed allocation is 54 hours for Temiko Machavariani and 46 for Nurtore Arynuruly. The course instructor accepts assessed deliverables and reviews material changes.